## Mechanical Electrical
RKN-08 [D]
MECHANICAL AND ELECTRICAL CONSULTING ENGINEER'S PERFORMANCE APPRAISAL
(Mechanical Electrical as Secondary Consultant)
CONSULTANT:
VOTE NO / PROJECT:
PROJECT STATUS:
Note: | [10 empty] | OIC:
1 | Type in score in BLUE cells only
2 | If not all criteria can be used yet e.g. project is still on-going delete appropriate BLUE and YELLOW cells to re-factor weights and score results
|  | CATEGORY | [8 empty] | NOTES | Score | Weights | Weighted Score | Weights to Use
GENERAL | 1 | Cooperation & Responsiveness
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | How consultant responds to instructions and requests of department, whether immediate response / very cooperative or delayed response / argumentative. Not applicable to consultant's appeal / refusal against instructions that diminishes consultant's professional standing and rights.
|  |  | Argumentative, not cooperative | 0 | 20 | 40 | 60 | 80 | 100 | Very cooperative and responsive |  |  | 4% | 0 | 4%
PRE-DESIGN | 2 | Mobilisation
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | How of consultant starts work, whether immediately or delays due to protracted negotiations of scope of services. (For purpose of appraisal, developing client brief is considered as work and not negotiation of services)
|  |  | Very slow mobilisation | 0 | 20 | 40 | 60 | 80 | 100 | Immediate mobilisation |  |  | 2% | 0 | 2%
| 3 | Project Site Investigation
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | Thorough site investigation minimises delays due to unseen issues such as unplanned relocation of services during implementation.
|  |  | Poor site investigation | 0 | 20 | 40 | 60 | 80 | 100 | Thorough site investigation |  |  | 6% | 0 | 6%
| 4 | Submission of Project Brief, Preliminary Design, Estimates to Project Architect / QS
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | Consultants should not be penalised for delays due to client or employer. If delays are entirely due to consultant, then as guide 1 month late = 50 pts; 2 months late = 0 pts; pro-rata the rest
|  |  | Very late | 0 | 20 | 40 | 60 | 80 | 100 | On time or Ahead |  |  | 5% | 0 | 5%
DESIGN | 5 | Submission of Detailed Design and Documentation to Project Architect / QS
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | As guide, 1 month late = 50 pts; 2 months late = 0 pts; pro-rata the rest
|  |  | Very late | 0 | 20 | 40 | 60 | 80 | 100 | Ahead of Schedule |  |  | 5% | 0 | 5%
| 6 | Technical Competence / Quality of Work
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | Quality of work of consultant, whether acceptable to department on first submission or requires department to advise extensive corrections and re-design.
|  |  | Too many amendments based on Employer's advice | 0 | 20 | 40 | 60 | 80 | 100 | Department did not have to give technical advice |  |  | 30% | 0 | 30%
| 7 | Completeness of Contribution to Tender Documents
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ►
|  |  | Incomplete | 0 | 20 | 40 | 60 | 80 | 100 | Complete |  |  | 5% | 0 | 5%
TENDER | 8 | Contribution to Tender Evaluation and Recommendation
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | Thoroughness of tender evaluation and recommendation based on technical assessment.
|  |  | Poor | 0 | 20 | 40 | 60 | 80 | 100 | Thorough |  |  | 5% | 0 | 5%
| 9 | Contribution to Pre-Tender Estimates
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | 100 pts for average of all tenders received <5% compared to engineer's pre-tender estimates; 80 pts >5% - <10%; 60 pts >10% - <15%; 40 pts >15% - <20%; 20 pts >20% - <25%; 0 pts >25%
|  |  | Poor pre-tender estimate | 0 | 20 | 40 | 60 | 80 | 100 | Excellent pre-tender estimate |  |  | 5% | 0 | 5%
CONSTRUCTION | 10 | Contribution to Site Coordination Meetings
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ►
|  |  | Ineffective | 0 | 20 | 40 | 60 | 80 | 100 | Effective |  |  | 3% | 0 | 3%
| 11 | Identification of Causes of Delays and Recommendation for Recovery
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ►
|  |  | Passive management; contractor-driven | 0 | 20 | 40 | 60 | 80 | 100 | Active leadership and management of contract |  |  | 4% | 0 | 4%
| 12 | Resolving Technical Issues and Physical Problems on Site
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | 100 pts for average of all tenders received <5% compared to engineer's pre-tender estimates; 80 pts >5% - <10%; 60 pts >10% - <15%; 40 pts >15% - <20%; 20 pts >20% - <25%; 0 pts >25%
|  |  | Poor | 0 | 20 | 40 | 60 | 80 | 100 | Excellent |  |  | 5% | 0 | 5%
| 13 | Regular Evaluation of Work Done On Site For Certifying Payments
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ►
|  |  | Irregular and delayed | 0 | 20 | 40 | 60 | 80 | 100 | Regular and On-Time |  |  | 2% | 0 | 2%
| 14 | Delays Due To Consultant's Oversight During Site Investigation and / or Design
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | 100 pts for jobs completed earlier than scheduled; 80 pts jobs on time; 60 pts 1% - 33% delayed; 40 pts 34% - 66 % delayed; 20 tps 67% - 99% delayed; 0 pts for jobs delayed 100% time and over. Only use ORIGINAL contract schedule as reference, not revised schedule
|  |  | Delays due to consultant's oversight and/or poor planning | 0 | 20 | 40 | 60 | 80 | 100 | No delays due to consultant's oversight and/or poor planning |  |  | 5% | 0 | 5%
| 15 | Contribution to Management of EOT Application
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | Generally if consultant takes more than 30 days = 0 pt.
|  |  | Late recommendation | 0 | 20 | 40 | 60 | 80 | 100 | Timely recommendation |  |  | 2% | 0 | 2%
POST-COMPLETION | 16 | Timely Completion
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | 100 pts for jobs completed earlier than scheduled; 80 pts jobs on time; 60 pts 1% - 33% delayed; 40 pts 34% - 66 % delayed; 20 tps 67% - 99% delayed; 0 pts for jobs delayed 100% time and over. Only use ORIGINAL contract schedule as reference, not revised schedule
|  |  | 100% time delay over schedule or more | 0 | 20 | 40 | 60 | 80 | 100 | Completed earlier than scheduled |  |  | 4% | 0 | 4%
| 17 | Contribution to Completion of Final Measurement / Submission of Penultimate Payment Certificate
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | More than 4 months = 0 pt.
|  |  | Delayed | 0 | 20 | 40 | 60 | 80 | 100 | Ahead of Schedule |  |  | 4% | 0 | 4%
| 18 | Contribution to Submission of Final Account
|  |  |  | ◄ | ◄ | ◄ | ► | ► | ► |  | I months beyond due date = 0 pt.
|  |  | Delayed | 0 | 20 | 40 | 60 | 80 | 100 | Ahead of Schedule |  |  | 4% | 0 | 4%
[13 empty] | 100% | 0 | 100%
[14 empty] | Re-factored Score | 0