QUOTATION NO. JUA25/028/SAB/KB

MISCELLANEOUS SURVEY OF THE LAND BOUNDARY ​

FOR  SECTOR B – C (IP 32 – IP 65),

BELAIT DISTRICT

SCHEDULE TO SPECIFICATION

- MISCELLANEOUS SURVEY OF THE LAND BOUNDARY ​FOR SECTOR B – C FROM IP 32 TO 
IP 65, BELAIT DISTRICT for An Approximate Total Distance Of 15.3 Km as shown on the Annex 1.

- The job MUST be completed in 7 weeks. The validity period of the quotation for the survey works is six (6) months. All quotations document shall be stamped and signed by the Licensed Land Surveyor.

- The Licensed Land Surveyor is required to liaise with the Bahagian Pengukuran Sempadan dan Hidrografi (PSH), Survey Department, Ministry of Development before starting of the project for exact location of the survey site, logistic arrangement and for further information.

- All the surveyors and staffs under the Licensed Surveyor involved in this project must be Bruneian with Yellow IC / Red IC. All the personnel name and IC number shall be listed in the document.

- Survey team shall have a minimum of seven (7) personnel consist of:

  - Survey Technician - two (2) person

  - General Workers - five (5) persons

- The Licensed Land Surveyor survey team will be working under the strict supervision and instruction of Survey Department personnel and only Assistant Survey Team Leader (ASTL) of the project are allowed to make direct discussion and recommendation to the counterpart surveyor.

- The Licensed Land Surveyor personnel must abide by the rules during their working period as stipulated in the specification. All camping equipment and logistic requirements will be borne by the Licensed Land Surveyor.

- The Licensed Land Surveyor shall be responsible for Health, Safety and Environment (HSE) of their personnel at all time.

- SCOPE OF WORKS

  - The purpose of this survey is to find old boundary markers located in Sector B - C (From IP 32 to IP 65) as shown in annex 1.

  - The Survey shall commence from and to existing control survey stations or trigonometrical stations with known planimetric and height values or from established boundary markers.

  - For adopted azimuth, observations to control survey stations or trigonometrical stations or established boundary markers are taken from the same Total Station using different zeros. If control survey stations or trigonometrical station is not possible, azimuth control may be obtained by Sun observation.

  - For angular observations, three zero settings shall be used for each horizontal angle observation:

    - Set 1 Face Left (FL) 00°

    - Set 2 Face Right (FR) 90°

    - Set 3 Face Left (FL) 225°

  - Station angle is the angle measured clockwise from the back target to the forward target. Three sets of angles have to be observed at every station as follow:

Every set:

i. FL of Back target

ii. FL of Forward target

iii. FR of Forward target

iv. FR of Back target

The sets of observation shall not differ by ± 5” seconds.

  - Traverse lines shall be measured by Electromagnetic Distance Measuring equipment with accuracy of ± (5 mm ± 5 ppm) m.s.e or better equipment.

  - Old boundary marker found, missing or damaged must be marked or staked and photographed from at least four different angles. Coordinates taken using handheld GPS must be included in the Survey Report.

  - The missing old boundary marker need not to be refixed nor replaced.

  - All the measurement and traverse diagram must be recorded in the government field book.

  - Survey must start/adopted and close to IP boundary markers and boundary markers are to be traversed directly; shooting observations to boundary markers are not permitted.

  - An additional Sun Observation for Azimuth Control (p.e. ± 10 ’’) at Control Survey stations at every interval (not exceeding 25 stations) for the line to be adopted.

- The relevant survey information will be provided by Bahagian Pengukuran Sempadan dan Hidrografi.

- Licensed Land Surveyor to attend the discussion with Bahagian Pengukuran Sempadan dan Hidrografi upon the commencement of the contract.

NOTICE TO THE CONTRACTOR

- To be supplied by Contractor.

- Copies of digital data shall be supplied by Contractor.

- Submission of JUA Project should be completed as the following:

- Survey Report

- Field Book

- Computation Sheets (softcopy and hardcopy)

- All Related Demarcation Survey Form (DSF) (softcopy and hardcopy)

- Miscellaneous plans will be plotted at a suitable scale showing all the information in A1 size (softcopy and hardcopy)

- The Surveyor General shall authorize the contractor to commence work, once the signing of the contract award letter.

- In the event of the contractor fail to complete the project, penalty starting at 5 % (five percent) of the project price according to the week of late submission will be imposed and referred to the table in the letter (Ruj: (01)dlm.SS/TOPO/G/40; Dated: 4 July 2020).

- Payment for the project will be made in two installments as follows:

- 60% of the total contract price will be paid upon completion of the Survey Work and after the contractor's pullout from the site, subject to verification by the Survey Department.

- The remaining 40% of the total contract price will be paid after  all deliverables have been approved by the Survey Department.

DECLARATION OF THE CONTRACTOR

- That I/We have not colluded with any other company (ies) or any other person or entity in submitting the Tender Proposal for the above-mentioned project. We understand that tender collusion is an offence under Section 11, Competition Order 2015 and can be liable to a financial penalty of maximum 10 percent or such other percentage of business turnover for each year of infringement for a period, up to a maximum of 3 years.

Annex 1

Annex 1

IP32

IP65

IP32

IP65

Total Distance from station IP32 to IP65 : Approximately 15.3km

Total Distance from station IP32 to IP65 : Approximately 15.3km