## Sheet1
IIP-01 [C]
PRE-TENDER REPORT
This report is to be filled by PRINCIPAL CONSULTANT. This report may be submitted by email to rkn.iip@mod.gov.bn. Submissions by email shall be deemed authorised by principals of the consultancy.
VOTE NUMBER |  |  | SCHEME VALUE
PROJECT TITLE
ARC
C&S
M&E
QS
REPORT FOR MONTH / YEAR
1 | DATE OF OFFER |  | OFFER DATE | ACCEPTANCE DATE
2 | DATE OF COMPLETION OF DESIGN BRIEF WITH CLIENT |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
3 | DATE OF COMPLETION OF PRELIMINARY DESIGN |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
4 | DATE OF PRELIMINARY DESIGN APPROVED BY CLIENT |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE
5 | DATE OF COMPLETION OF WORKING DRAWINGS AND TENDER DOCUMENTATION |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
6 | DATE OF CALLING TENDER |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
7 | DATE OF CLOSING TENDER |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
8 | DATE OF SUBMISSION OF TENDER EVALUATION |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
9 | DATE OF TENDER APPROVAL |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
10 | DATE OF CONTRACT COMMENCEMENT |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
11 | DATE OF CONTRACT COMPLETION |  | TARGET DATE | ACTUAL DATE
REASONS FOR DELAY / CHANGE OF TARGET DATE :
12 | PROJECT COMPLETION DATE |  | TARGET DATE